# I. ONGOING PROJECT WORKS

## NEW GRAIN MARKET, NARELA

| S.No. | Name of Work | Brief Description | Earnest Money (Rs.) | Work Awarded to | Date of Award of work | Estimated cost (Rs.) | Time of completion | Actual expenditure incurred (Rs.) | Date of actual completion | Current Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Planning and redesigning of NGM Narela | - | - | - | - | 44.72 crores | - | - | - | - New Architect/Consultant M/s ARCH-EN-DESIGN has been appointed and the work of re-designing of NGM, Narela is in progress. |

## IFC GAZIPUR

| S.No. | Name of Work | Brief Description | Earnest Money (Rs.) | Work Awarded to | Date of Award of work | Estimated cost (Rs.) | Time of completion | Actual expenditure incurred (Rs.) | Date of actual completion | Current Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Development of Fruit, Vegetable & Grain Market at IFC, Gazipur | - | - | - | - | - | - | - | - | - The work on the Phase-I , II & III-A (9th Block) has been completed. - The work of Phase III-B is to be started after shifting of traders of the new yard. |
| 2. | Setting up of Wholesale Flower Market at IFC, Gazipur | AS decided by the Board Flower Mkt. is to be developed in 9.97 acres area which is part of F/V & Grain Market,IFC Gazipur. M/s Arch-En- Design has been appointed as Consultant. | - | - | - | - | - | - | - | - Layout and building plans for flower market have been submitted to the Local Authorities for their approval. |

## FP&EMC, GAZIPUR

| S.No. | Name of Work | Brief Description | Earnest Money (Rs.) | Work Awarded to | Date of Award of work | Estimated cost (Rs.) | Time of completion | Actual expenditure incurred (Rs.) | Date of actual completion |  | Current Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Setting up of Mechanized Chicken Dressing Plant at Gazipur on PPP |  |  |  |  | 73.86 crores |  |  |  | - Cabinet approved the proposal for setting up of Mechanized Chicken Dressing Plant on PPP Model. Accordingly, tenders were invited. Bids have been invited for three times during 1st & 3rd call only single bid was received and during 2nd call no bid was received. Finally the proposal could not be materialized. The proposal is under consideration of the Competent Authority to increase the participation of bidders as well as sanctioned plans are yet to be released by building section of DDA. Thereafter the proposal to be taken up again accordingly. |  |
| 2. | Development of Modern Poultry Market at Gazipur | - | - | - | - | 129.00 Crores | - | - | - |  | The lay out plans and building plans have been cleared by local authorities i.e. DUAC, DFS, DJB & DPCC . Environmental clearance has been obtained from Ministry of Environment & Forest, Govt. of India. Sanctioned Plans have not yet been released by Building Section of DDA for want of Time Extension from land section of DDA. Detailed estimate in respect of civil and electrical works have been submitted by the Architect. DAMB has deposited the composition fee as demanded by DDA but now the DDA demanded additional Composition Fee the matter has taken up the matter for settlement of composition fee with DDA. |

## RAJENDRA PLACE, GUEST HOUSE

| S.No. | Name of Work | Brief Description | Earnest Money (Rs.) | Work Awarded to | Date of Award of work | Estimated cost (Rs.) | Time of completion | Actual expenditure incurred (Rs.) | Date of actual completion | Current Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Repair and Renovation of Guest House at Rajendra Place | - | 40,200/- | M/s. Ess DEE Construction | - | 20,10,000/- | 5 months | - | - | Work under process for award of work |

## APMC , AZADPUR

| S.No. | Name of Work | Brief Description | Earnest Money (Rs.) | Work Awarded to | Date of Award of work | Estimated cost (Rs.) | Time of completion | Actual expenditure incurred (Rs.) | Date of actual completion | Current Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Setting up of wholesale Fruit & Vegetable Market at Tikri Khampur | - | - | - | - | 900.00 crores (tentative) | - | - | - | - There is a Court Case related to compost plant which is interfering the Planning work of the mandi and likely to be shifted in mandi premises. - Secretary, APMC Azadpur has suggested that the project shall be taken up on self financing scheme. Final decision is to be taken by the Competent Authority. |
| 2. | Computerization of APMC, Azadpur | - | - | - | - | - | - | - | - | - Birla Soft is developing the software for IMMS (Integrated Mandi Management System). - Tender document for procurement of Hardware has been got vetted by the NIC as advised by the IT Department of Govt. of NCT of Delhi. APMC, Azadpur is floating tender for Hardware. |
| 3. | Remodeling of New Fruit Mkt. area at NFM Azadpur. |  |  |  |  | 200 crores (tentative) |  |  |  | - Appointment of Architect is to be done after Tikri Khampur Project. |